## Folha1
Backlog ID | User Story ID | Estimated Effort | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Update Scrum_Master_Log | 1 | 1 | bar: Day 2
Update Scrum_board with Sprint 3 | 2 | 1 | bar: Day 6
Create User story for feature 1 | 3 | 2 | bar: Day 5 to Day 6
Create User story for feature 2 | 4 | 2 | bar: Day 5 to Day 6
Correct problems in the use case diagrams | 5 | 2 | bar: Day 4 to Day 5
Update Git with the files that were modified | 6 | 2 | bar: Day 4 to Day 5
Review the metrics set report of team member 1 | 7 | 2 | bar: Day 4 to Day 5
Review the metrics set report of team member 2 | 8 | 2 | bar: Day 4 to Day 5
Review the metrics set report of team member 3 | 9 | 2 | bar: Day 4 to Day 5
Review the metrics set report of team member 4 | 10 | 2 | bar: Day 4 to Day 5
Review the metrics set report of team member 5 | 11 | 2 | bar: Day 4 to Day 5
Implement Feature 1 (Burndown Chart) | 12 | 4 | bar: Day 2 to Day 5
Add an option with XLSX file to the export alternatives. | 13 | 3 | Day 2: 2; Day 5: 1
Get the informations from all the tasks. | 14 | 4 | Day 3: 2; Day 4: 1; Day 5: 1
Use the data from the tasks to create the burndown chart. | 15 | 3 | bar: Day 3 to Day 5
Edit the looks of the chart to be more look alike a burndown chart. | 16 | 4 | bar: Day 2 to Day 5
Implement Feature 2 (Google Calendar Integration) | 17 | 4 | bar: Day 2 to Day 5
Make the needed dependencies work | 18 | 6 | Day 2: 2; Day 3: 1; Day 4: 2; Day 5: 1
Add "Google Calendar" option in the export options | 19 | 2 | bar: Day 4 to Day 5
Add functionality for the user to login or if already loggen in to change account | 20 | 2 | bar: Day 4 to Day 5
Add button to help the user interact with login functionalities | 21 | 2 | bar: Day 4 to Day 5
Remove document browser in the second step of the export functionality | 22 | 2 | bar: Day 2 to Day 3
As the user clicks "Ok", create events in Google Calendar of the logged in user | 23 | 2 | bar: Day 4 to Day 5
Don't allow the user to export to Google Calendar if no account is connected | 24 | 2 | bar: Day 4 to Day 5
Create J-Unit Tests | 25 | 2 | bar: Day 5 to Day 6
Record Video | 26 | 1 | bar: Day 6
| Idealized Burn | 63 | 54 | 45 | 36 | 27 | 18 | 9 | 0
| Actual burned | 63 | 63 | 54 | 46 | 27 | 5 | 0 | 0