## Fase 1 - Sprint1
Day 1 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Identificar Design Patterns | x |  |  |  | Every Member
| Identificar Smell Codes | x |  |  |  | Every Member
| Fazer revisão do trabalho do respetivo colega | x |  |  |  | Every Member
| Criar MergeDoc com os code Smells e Patterns todos | x |  |  |  | Francisco Vale
| Criar MergeDoc com as reviews todos | x |  |  |  | Tiago Francisco
| Criar Sprint Backlog |  | x |  |  | Guilherme Franco
| Criar BurnOutChart |  | x |  |  | Guilherme Franco
| Criar Scrum Master Log | x |  |  |  | Luís Abreu
| Criar Work Breakdown Structure | x |  |  |  | Pedro Gouveia
Day 2 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Identificar Design Patterns |  | x |  |  | Every Member
| Identificar Smell Codes |  | x |  |  | Every Member
| Fazer revisão do trabalho do respetivo colega | x |  |  |  | Every Member
| Criar MergeDoc com os code Smells e Patterns todos | x |  |  |  | Francisco Vale
| Criar MergeDoc com as reviews todos | x |  |  |  | Tiago Francisco
| Criar Sprint Backlog |  |  |  | x | Guilherme Franco
| Criar BurnOutChart |  |  |  | x | Guilherme Franco
| Criar Scrum Master Log | x |  |  |  | Luís Abreu
| Criar Work Breakdown Structure | x |  |  |  | Pedro Gouveia
Day 3 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Identificar Design Patterns |  | x |  |  | Every Member
| Identificar Smell Codes |  | x |  |  | Every Member
| Fazer revisão do trabalho do respetivo colega | x |  |  |  | Every Member
| Criar MergeDoc com os code Smells e Patterns todos | x |  |  |  | Francisco Vale
| Criar MergeDoc com as reviews todos | x |  |  |  | Tiago Francisco
| Criar Sprint Backlog |  |  |  | x | Guilherme Franco
| Criar BurnOutChart |  |  |  | x | Guilherme Franco
| Criar Scrum Master Log | x |  |  |  | Luís Abreu
| Criar Work Breakdown Structure | x |  |  |  | Pedro Gouveia
Day 4 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Identificar Design Patterns |  | x |  |  | Every Member
| Identificar Smell Codes |  | x |  |  | Every Member
| Fazer revisão do trabalho do respetivo colega |  | x |  |  | Every Member
| Criar MergeDoc com os code Smells e Patterns todos | x |  |  |  | Francisco Vale
| Criar MergeDoc com as reviews todos | x |  |  |  | Tiago Francisco
| Criar Sprint Backlog |  |  |  | x | Guilherme Franco
| Criar BurnOutChart |  |  |  | x | Guilherme Franco
| Criar Scrum Master Log | x |  |  |  | Luís Abreu
| Criar Work Breakdown Structure | x |  |  |  | Pedro Gouveia
Day 5 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Identificar Design Patterns |  |  | x |  | Every Member
| Identificar Smell Codes |  |  | x |  | Every Member
| Fazer revisão do trabalho do respetivo colega |  | x |  |  | Every Member
| Criar MergeDoc com os code Smells e Patterns todos | x |  |  |  | Francisco Vale
| Criar MergeDoc com as reviews todos | x |  |  |  | Tiago Francisco
| Criar Sprint Backlog |  |  |  | x | Guilherme Franco
| Criar BurnOutChart |  |  |  | x | Guilherme Franco
| Criar Scrum Master Log | x |  |  |  | Luís Abreu
| Criar Work Breakdown Structure | x |  |  |  | Pedro Gouveia
Day 6 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Identificar Design Patterns |  |  |  | x | Every Member
| Identificar Smell Codes |  |  |  | x | Every Member
| Fazer revisão do trabalho do respetivo colega |  |  | x |  | Every Member
| Criar MergeDoc com os code Smells e Patterns todos |  |  | x |  | Francisco Vale
| Criar MergeDoc com as reviews todos | x |  |  |  | Tiago Francisco
| Criar Sprint Backlog |  |  |  | x | Guilherme Franco
| Criar BurnOutChart |  |  |  | x | Guilherme Franco
| Criar Scrum Master Log |  | x |  |  | Luís Abreu
| Criar Work Breakdown Structure |  | x |  |  | Pedro Gouveia
Day 7 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Identificar Design Patterns |  |  |  | x | Every Member
| Identificar Smell Codes |  |  |  | x | Every Member
| Fazer revisão do trabalho do respetivo colega |  |  |  | x | Every Member
| Criar MergeDoc com os code Smells e Patterns todos |  |  |  | x | Francisco Vale
| Criar MergeDoc com as reviews todos |  |  |  | x | Tiago Francisco
| Criar Sprint Backlog |  |  |  | x | Guilherme Franco
| Criar BurnOutChart |  |  |  | x | Guilherme Franco
| Criar Scrum Master Log |  |  |  | x | Luís Abreu
| Criar Work Breakdown Structure |  |  |  | x | Pedro Gouveia

## Fase 2 - Sprint1
Day 1 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Distribute use cases of the ganttproject between the members | X |  |  |  | Every Member
| Create report about use case, must have the diagram and all the details about the use case set 1 | X |  |  |  | Luís Abreu
| Create report about use case, must have the diagram and all the details about the use case set 2 | X |  |  |  | Tiago Francisco
| Create report about use case, must have the diagram and all the details about the use case set 3 | X |  |  |  | Guilherme Franco
| Create report about use case, must have the diagram and all the details about the use case set 4 | X |  |  |  | Pedro Gouveia
| Create report about use case, must have the diagram and all the details about the use case set 5 | X |  |  |  | Francisco Vale
| Review the use case diagram and its analysis of a member team member 1 | X |  |  |  | Francisco Vale
| Review the use case diagram and its analysis of a member team member 2 | X |  |  |  | Pedro Gouveia
| Review the use case diagram and its analysis of a member team member 3 | X |  |  |  | Tiago Francisco
| Review the use case diagram and its analysis of a member team member 4 | X |  |  |  | Guilherme Franco
| Review the use case diagram and its analysis of a member team member 5 | X |  |  |  | Luís Abreu
Day 2 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Distribute use cases of the ganttproject between the members |  |  |  | X | Every Member
| Create report about use case, must have the diagram and all the details about the use case set 1 | X |  |  |  | Luís Abreu
| Create report about use case, must have the diagram and all the details about the use case set 2 | X |  |  |  | Tiago Francisco
| Create report about use case, must have the diagram and all the details about the use case set 3 | X |  |  |  | Guilherme Franco
| Create report about use case, must have the diagram and all the details about the use case set 4 | X |  |  |  | Pedro Gouveia
| Create report about use case, must have the diagram and all the details about the use case set 5 | X |  |  |  | Francisco Vale
| Review the use case diagram and its analysis of a member team member 1 | X |  |  |  | Francisco Vale
| Review the use case diagram and its analysis of a member team member 2 | X |  |  |  | Pedro Gouveia
| Review the use case diagram and its analysis of a member team member 3 | X |  |  |  | Tiago Francisco
| Review the use case diagram and its analysis of a member team member 4 | X |  |  |  | Guilherme Franco
| Review the use case diagram and its analysis of a member team member 5 | X |  |  |  | Luís Abreu
Day 3 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Distribute use cases of the ganttproject between the members |  |  |  | X | Every Member
| Create report about use case, must have the diagram and all the details about the use case set 1 |  | X |  |  | Luís Abreu
| Create report about use case, must have the diagram and all the details about the use case set 2 |  | X |  |  | Tiago Francisco
| Create report about use case, must have the diagram and all the details about the use case set 3 |  | X |  |  | Guilherme Franco
| Create report about use case, must have the diagram and all the details about the use case set 4 |  | X |  |  | Pedro Gouveia
| Create report about use case, must have the diagram and all the details about the use case set 5 | X |  |  |  | Francisco Vale
| Review the use case diagram and its analysis of a member team member 1 | X |  |  |  | Francisco Vale
| Review the use case diagram and its analysis of a member team member 2 | X |  |  |  | Pedro Gouveia
| Review the use case diagram and its analysis of a member team member 3 | X |  |  |  | Tiago Francisco
| Review the use case diagram and its analysis of a member team member 4 | X |  |  |  | Guilherme Franco
| Review the use case diagram and its analysis of a member team member 5 | X |  |  |  | Luís Abreu
Day 4 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Distribute use cases of the ganttproject between the members |  |  |  | X | Every Member
| Create report about use case, must have the diagram and all the details about the use case set 1 |  |  |  | X | Luís Abreu
| Create report about use case, must have the diagram and all the details about the use case set 2 |  |  |  | X | Tiago Francisco
| Create report about use case, must have the diagram and all the details about the use case set 3 |  |  |  | X | Guilherme Franco
| Create report about use case, must have the diagram and all the details about the use case set 4 |  |  |  | X | Pedro Gouveia
| Create report about use case, must have the diagram and all the details about the use case set 5 | X |  |  |  | Francisco Vale
| Review the use case diagram and its analysis of a member team member 1 | X |  |  |  | Francisco Vale
| Review the use case diagram and its analysis of a member team member 2 | X |  |  |  | Pedro Gouveia
| Review the use case diagram and its analysis of a member team member 3 | X |  |  |  | Tiago Francisco
| Review the use case diagram and its analysis of a member team member 4 | X |  |  |  | Guilherme Franco
| Review the use case diagram and its analysis of a member team member 5 | X |  |  |  | Luís Abreu
Day 5 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Distribute use cases of the ganttproject between the members |  |  |  | X | Every Member
| Create report about use case, must have the diagram and all the details about the use case set 1 |  |  |  | X | Luís Abreu
| Create report about use case, must have the diagram and all the details about the use case set 2 |  |  |  | X | Tiago Francisco
| Create report about use case, must have the diagram and all the details about the use case set 3 |  |  |  | X | Guilherme Franco
| Create report about use case, must have the diagram and all the details about the use case set 4 |  |  |  | X | Pedro Gouveia
| Create report about use case, must have the diagram and all the details about the use case set 5 |  | X |  |  | Francisco Vale
| Review the use case diagram and its analysis of a member team member 1 |  | X |  |  | Francisco Vale
| Review the use case diagram and its analysis of a member team member 2 |  | X |  |  | Pedro Gouveia
| Review the use case diagram and its analysis of a member team member 3 |  | X |  |  | Tiago Francisco
| Review the use case diagram and its analysis of a member team member 4 |  | X |  |  | Guilherme Franco
| Review the use case diagram and its analysis of a member team member 5 | X |  |  |  | Luís Abreu
Day 6 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Distribute use cases of the ganttproject between the members |  |  |  | X | Every Member
| Create report about use case, must have the diagram and all the details about the use case set 1 |  |  |  | X | Luís Abreu
| Create report about use case, must have the diagram and all the details about the use case set 2 |  |  |  | X | Tiago Francisco
| Create report about use case, must have the diagram and all the details about the use case set 3 |  |  |  | X | Guilherme Franco
| Create report about use case, must have the diagram and all the details about the use case set 4 |  |  |  | X | Pedro Gouveia
| Create report about use case, must have the diagram and all the details about the use case set 5 |  |  |  | X | Francisco Vale
| Review the use case diagram and its analysis of a member team member 1 |  | X |  |  | Francisco Vale
| Review the use case diagram and its analysis of a member team member 2 |  |  |  | X | Pedro Gouveia
| Review the use case diagram and its analysis of a member team member 3 |  |  |  | X | Tiago Francisco
| Review the use case diagram and its analysis of a member team member 4 |  |  |  | X | Guilherme Franco
| Review the use case diagram and its analysis of a member team member 5 |  |  |  | X | Luís Abreu
Day 7 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Distribute use cases of the ganttproject between the members |  |  |  | X | Every Member
| Create report about use case, must have the diagram and all the details about the use case set 1 |  |  |  | X | Luís Abreu
| Create report about use case, must have the diagram and all the details about the use case set 2 |  |  |  | X | Tiago Francisco
| Create report about use case, must have the diagram and all the details about the use case set 3 |  |  |  | X | Guilherme Franco
| Create report about use case, must have the diagram and all the details about the use case set 4 |  |  |  | X | Pedro Gouveia
| Create report about use case, must have the diagram and all the details about the use case set 5 |  |  |  | X | Francisco Vale
| Review the use case diagram and its analysis of a member team member 1 |  |  |  | X | Francisco Vale
| Review the use case diagram and its analysis of a member team member 2 |  |  |  | X | Pedro Gouveia
| Review the use case diagram and its analysis of a member team member 3 |  |  |  | X | Tiago Francisco
| Review the use case diagram and its analysis of a member team member 4 |  |  |  | X | Guilherme Franco
| Review the use case diagram and its analysis of a member team member 5 |  |  |  | X | Luís Abreu

## Fase 2 - Sprint2
Day 1 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Update Scrum_Master_Log | X |  |  |  | Guilherme Franco
| Update Scrum_board | X |  |  |  | Luís Abreu ¦ Guilherme Franco
| Create first Sprint_Backlog | X |  |  |  | Luís Abreu ¦ Guilherme Franco
| Create second Sprint_Backlog | X |  |  |  | Luís Abreu ¦ Guilherme Franco
| Distribute metrics between the members | X |  |  |  | Every Member
| Create Report about metrics set 1 | X |  |  |  | Luís Abreu
| Create Report about metrics set 2 | X |  |  |  | Tiago Francisco
| Create Report about metrics set 3 | X |  |  |  | Guilherme Franco
| Create Report about metrics set 4 | X |  |  |  | Pedro Gouveia
| Create Report about metrics set 5 | X |  |  |  | Francisco Vale
| Review the metrics set report of team member 1 | X |  |  |  | Francisco Vale
| Review the metrics set report of team member 2 | X |  |  |  | Pedro Gouveia
| Review the metrics set report of team member 3 | X |  |  |  | Tiago Francisco
| Review the metrics set report of team member 4 | X |  |  |  | Guilherme Franco
| Review the metrics set report of team member 5 | X |  |  |  | Luís Abreu
Day 2 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Update Scrum_Master_Log |  | X |  |  | Guilherme Franco
| Update Scrum_board |  | X |  |  | Luís Abreu ¦ Guilherme Franco
| Create first Sprint_Backlog |  | X |  |  | Luís Abreu ¦ Guilherme Franco
| Create second Sprint_Backlog |  | X |  |  | Luís Abreu
| Distribute metrics between the members |  | X |  |  | Every Member
| Create Report about metrics set 1 | X |  |  |  | Tiago Francisco
| Create Report about metrics set 2 | X |  |  |  | Guilherme Franco
| Create Report about metrics set 3 | X |  |  |  | Pedro Gouveia
| Create Report about metrics set 4 | X |  |  |  | Francisco Vale
| Create Report about metrics set 5 | X |  |  |  | Luís Abreu
| Review the metrics set report of team member 1 | X |  |  |  | Luís Abreu
| Review the metrics set report of team member 2 | X |  |  |  | Tiago Francisco
| Review the metrics set report of team member 3 | X |  |  |  | Guilherme Franco
| Review the metrics set report of team member 4 | X |  |  |  | Pedro Gouveia
| Review the metrics set report of team member 5 | X |  |  |  | Francisco Vale
Day 3 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Update Scrum_Master_Log |  |  |  | X | Guilherme Franco
| Update Scrum_board |  |  |  | X | Luís Abreu ¦ Guilherme Franco
| Create first Sprint_Backlog |  |  |  | X | Luís Abreu ¦ Guilherme Franco
| Create second Sprint_Backlog |  |  |  | X | Luís Abreu
| Distribute metrics between the members |  |  |  | X | Every Member
| Create Report about metrics set 1 |  | X |  |  | Tiago Francisco
| Create Report about metrics set 2 |  | X |  |  | Guilherme Franco
| Create Report about metrics set 3 |  | X |  |  | Pedro Gouveia
| Create Report about metrics set 4 |  | X |  |  | Francisco Vale
| Create Report about metrics set 5 |  | X |  |  | Every Member
| Review the metrics set report of team member 1 | X |  |  |  | Luís Abreu
| Review the metrics set report of team member 2 | X |  |  |  | Tiago Francisco
| Review the metrics set report of team member 3 | X |  |  |  | Guilherme Franco
| Review the metrics set report of team member 4 | X |  |  |  | Pedro Gouveia
| Review the metrics set report of team member 5 | X |  |  |  | Francisco Vale
Day 4 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Update Scrum_Master_Log |  |  |  | X | Guilherme Franco
| Update Scrum_board |  |  |  | X | Luís Abreu ¦ Guilherme Franco
| Create first Sprint_Backlog |  |  |  | X | Luís Abreu ¦ Guilherme Franco
| Create second Sprint_Backlog |  |  |  | X | Luís Abreu
| Distribute metrics between the members |  |  |  | X | Every Member
| Create Report about metrics set 1 |  |  |  | X | Tiago Francisco
| Create Report about metrics set 2 |  |  |  | X | Guilherme Franco
| Create Report about metrics set 3 |  |  |  | X | Pedro Gouveia
| Create Report about metrics set 4 |  |  |  | X | Francisco Vale
| Create Report about metrics set 5 |  |  |  | X | Every Member
| Review the metrics set report of team member 1 | X |  |  |  | Luís Abreu
| Review the metrics set report of team member 2 | X |  |  |  | Tiago Francisco
| Review the metrics set report of team member 3 | X |  |  |  | Guilherme Franco
| Review the metrics set report of team member 4 | X |  |  |  | Pedro Gouveia
| Review the metrics set report of team member 5 | X |  |  |  | Francisco Vale
Day 5 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Update Scrum_Master_Log |  |  |  | X | Guilherme Franco
| Update Scrum_board |  |  |  | X | Luís Abreu ¦ Guilherme Franco
| Create first Sprint_Backlog |  |  |  | X | Luís Abreu ¦ Guilherme Franco
| Create second Sprint_Backlog |  |  |  | X | Luís Abreu
| Distribute metrics between the members |  |  |  | X | Every Member
| Create Report about metrics set 1 |  |  |  | X | Tiago Francisco
| Create Report about metrics set 2 |  |  |  | X | Guilherme Franco
| Create Report about metrics set 3 |  |  |  | X | Pedro Gouveia
| Create Report about metrics set 4 |  |  |  | X | Francisco Vale
| Create Report about metrics set 5 |  |  |  | X | Every Member
| Review the metrics set report of team member 1 |  | X |  |  | Luís Abreu
| Review the metrics set report of team member 2 |  | X |  |  | Tiago Francisco
| Review the metrics set report of team member 3 |  | X |  |  | Guilherme Franco
| Review the metrics set report of team member 4 |  | X |  |  | Pedro Gouveia
| Review the metrics set report of team member 5 |  | X |  |  | Francisco Vale
Day 6 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Update Scrum_Master_Log |  |  |  | X | Guilherme Franco
| Update Scrum_board |  |  |  | X | Luís Abreu ¦ Guilherme Franco
| Create first Sprint_Backlog |  |  |  | X | Luís Abreu ¦ Guilherme Franco
| Create second Sprint_Backlog |  |  |  | X | Luís Abreu
| Distribute metrics between the members |  |  |  | X | Every Member
| Create Report about metrics set 1 |  |  |  | X | Tiago Francisco
| Create Report about metrics set 2 |  |  |  | X | Guilherme Franco
| Create Report about metrics set 3 |  |  |  | X | Pedro Gouveia
| Create Report about metrics set 4 |  |  |  | X | Francisco Vale
| Create Report about metrics set 5 |  |  |  | X | Every Member
| Review the metrics set report of team member 1 |  |  | X |  | Luís Abreu
| Review the metrics set report of team member 2 |  |  | X |  | Tiago Francisco
| Review the metrics set report of team member 3 |  |  | X |  | Guilherme Franco
| Review the metrics set report of team member 4 |  |  | X |  | Pedro Gouveia
| Review the metrics set report of team member 5 |  |  | X |  | Francisco Vale
Day 7 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Update Scrum_Master_Log |  |  |  | X | Guilherme Franco
| Update Scrum_board |  |  |  | X | Luís Abreu ¦ Guilherme Franco
| Create first Sprint_Backlog |  |  |  | X | Luís Abreu ¦ Guilherme Franco
| Create second Sprint_Backlog |  |  |  | X | Luís Abreu
| Distribute metrics between the members |  |  |  | X | Every Member
| Create Report about metrics set 1 |  |  |  | X | Tiago Francisco
| Create Report about metrics set 2 |  |  |  | X | Guilherme Franco
| Create Report about metrics set 3 |  |  |  | X | Pedro Gouveia
| Create Report about metrics set 4 |  |  |  | X | Francisco Vale
| Create Report about metrics set 5 |  |  |  | X | Every Member
| Review the metrics set report of team member 1 |  |  |  | X | Luís Abreu
| Review the metrics set report of team member 2 |  |  |  | X | Tiago Francisco
| Review the metrics set report of team member 3 |  |  |  | X | Guilherme Franco
| Review the metrics set report of team member 4 |  |  |  | X | Pedro Gouveia
| Review the metrics set report of team member 5 |  |  |  | X | Francisco Vale

## Fase 2 - Sprint3
Day 1 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Update Scrum_Master_Log | X |  |  |  | Guilherme Franco
| Update Scrum_board with Sprint 3 | X |  |  |  | Luís Abreu
| Create User story for feature 1 | X |  |  |  | Francisco Vale
| Create User story for feature 2 | X |  |  |  | Pedro Gouveia
| Correct problems in the use case diagrams | X |  |  |  | Every member
| Update Git with the files that were modified | X |  |  |  | Luís Abreu ¦ Guilherme Franco
| Review the metrics set report of team member 1 | X |  |  |  | Luís Abreu
| Review the metrics set report of team member 2 | X |  |  |  | Guilherme Franco
| Review the metrics set report of team member 3 | X |  |  |  | Pedro Gouveia
| Review the metrics set report of team member 4 | X |  |  |  | Tiago Francisco
| Review the metrics set report of team member 5 | X |  |  |  | Francisco Vale
| Implement Feature 1 (Burndown Chart) | X |  |  |  | Francisco Vale ¦ Guilherme Franco
| Add an option with XLSX file to the export alternatives. | X |  |  |  | Guilherme Franco
| Get the informations from all the tasks. | X |  |  |  | Francisco Vale
| Use the data from the tasks to create the burndown chart. | X |  |  |  | Francisco Vale
| Edit the looks of the chart to be more look alike a burndown chart. | X |  |  |  | Francisco Vale
| Implement Feature 2 (Google Calendar Integration) | X |  |  |  | Pedro Gouveia ¦ Tiago Francisco ¦ Luís Abreu
| Make the needed dependencies work | X |  |  |  | Pedro Gouveia
| Add "Google Calendar" option in the export options | X |  |  |  | Luís Abreu
| Add functionality for the user to login or if already loggen in to change account | X |  |  |  | Pedro Gouveia
| Add button to help the user interact with login functionalities | X |  |  |  | Tiago Francisco
| Remove document browser in the second step of the export functionality | X |  |  |  | Luís Abreu
| As the user clicks "Ok", create events in Google Calendar of the logged in user | X |  |  |  | Pedro Gouveia
| Don't allow the user to export to Google Calendar if no account is connected | X |  |  |  | Tiago Francisco
| Create J-Unit Tests | X |  |  |  | Every member
| Record Video | X |  |  |  | Every Member
Day 2 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Update Scrum_Master_Log |  | X |  |  | Guilherme Franco
| Update Scrum_board with Sprint 3 | X |  |  |  | Luís Abreu
| Create User story for feature 1 | X |  |  |  | Francisco Vale
| Create User story for feature 2 | X |  |  |  | Pedro Gouveia
| Correct problems in the use case diagrams | X |  |  |  | Every member
| Update Git with the files that were modified |  | X |  |  | Luís Abreu ¦ Guilherme Franco
| Review the metrics set report of team member 1 |  | X |  |  | Luís Abreu
| Review the metrics set report of team member 2 |  | X |  |  | Guilherme Franco
| Review the metrics set report of team member 3 |  | X |  |  | Pedro Gouveia
| Review the metrics set report of team member 4 |  | X |  |  | Tiago Francisco
| Review the metrics set report of team member 5 |  | X |  |  | Francisco Vale
| Implement Feature 1 (Burndown Chart) |  | X |  |  | Francisco Vale ¦ Guilherme Franco
| Add an option with XLSX file to the export alternatives. |  | X |  |  | Guilherme Franco
| Get the informations from all the tasks. | X |  |  |  | Francisco Vale
| Use the data from the tasks to create the burndown chart. | X |  |  |  | Francisco Vale
| Edit the looks of the chart to be more look alike a burndown chart. |  | X |  |  | Francisco Vale
| Implement Feature 2 (Google Calendar Integration) |  | X |  |  | Pedro Gouveia ¦ Tiago Francisco ¦ Luís Abreu
| Make the needed dependencies work |  | X |  |  | Pedro Gouveia
| Add "Google Calendar" option in the export options | X |  |  |  | Luís Abreu
| Add functionality for the user to login or if already loggen in to change account | X |  |  |  | Pedro Gouveia
| Add button to help the user interact with login functionalities | X |  |  |  | Tiago Francisco
| Remove document browser in the second step of the export functionality | X | X |  |  | Luís Abreu
| As the user clicks "Ok", create events in Google Calendar of the logged in user |  |  |  |  | Pedro Gouveia
| Don't allow the user to export to Google Calendar if no account is connected |  | X |  |  | Tiago Francisco
| Create J-Unit Tests | X |  |  |  | Every member
| Record Video | X |  |  |  | Every Member
Day 3 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Update Scrum_Master_Log |  |  |  | X | Guilherme Franco
| Update Scrum_board with Sprint 3 | X |  |  |  | Luís Abreu
| Create User story for feature 1 | X |  |  |  | Francisco Vale
| Create User story for feature 2 | X |  |  |  | Pedro Gouveia
| Correct problems in the use case diagrams | X |  |  |  | Every member
| Update Git with the files that were modified | X |  |  |  | Luís Abreu ¦ Guilherme Franco
| Review the metrics set report of team member 1 | X |  |  |  | Luís Abreu
| Review the metrics set report of team member 2 | X |  |  |  | Guilherme Franco
| Review the metrics set report of team member 3 | X |  |  |  | Pedro Gouveia
| Review the metrics set report of team member 4 | X |  |  |  | Tiago Francisco
| Review the metrics set report of team member 5 | X |  |  |  | Francisco Vale
| Implement Feature 1 (Burndown Chart) |  | X |  |  | Francisco Vale ¦ Guilherme Franco
| Add an option with XLSX file to the export alternatives. |  | X |  |  | Guilherme Franco
| Get the informations from all the tasks. |  | X |  |  | Francisco Vale
| Use the data from the tasks to create the burndown chart. |  | X |  |  | Francisco Vale
| Edit the looks of the chart to be more look alike a burndown chart. |  | X |  |  | Francisco Vale
| Implement Feature 2 (Google Calendar Integration) |  | X |  |  | Pedro Gouveia ¦ Tiago Francisco ¦ Luís Abreu
| Make the needed dependencies work |  | X |  |  | Pedro Gouveia
| Add "Google Calendar" option in the export options | X |  |  |  | Luís Abreu
| Add functionality for the user to login or if already loggen in to change account | X |  |  |  | Pedro Gouveia
| Add button to help the user interact with login functionalities | X |  |  |  | Tiago Francisco
| Remove document browser in the second step of the export functionality |  |  | X |  | Luís Abreu
| As the user clicks "Ok", create events in Google Calendar of the logged in user | X |  |  |  | Pedro Gouveia
| Don't allow the user to export to Google Calendar if no account is connected | X |  |  |  | Tiago Francisco
| Create J-Unit Tests | X |  |  |  | Every member
| Record Video | X |  |  |  | Every Member
Day 4 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Update Scrum_Master_Log |  |  |  | X | Guilherme Franco
| Update Scrum_board with Sprint 3 | X |  |  |  | Luís Abreu
| Create User story for feature 1 | X |  |  |  | Francisco Vale
| Create User story for feature 2 | X |  |  |  | Pedro Gouveia
| Correct problems in the use case diagrams |  | X |  |  | Every member
| Update Git with the files that were modified |  | X |  |  | Luís Abreu ¦ Guilherme Franco
| Review the metrics set report of team member 1 |  | X |  |  | Luís Abreu
| Review the metrics set report of team member 2 |  | X |  |  | Guilherme Franco
| Review the metrics set report of team member 3 |  | X |  |  | Pedro Gouveia
| Review the metrics set report of team member 4 |  | X |  |  | Tiago Francisco
| Review the metrics set report of team member 5 |  | X |  |  | Francisco Vale
| Implement Feature 1 (Burndown Chart) |  | X |  |  | Francisco Vale ¦ Guilherme Franco
| Add an option with XLSX file to the export alternatives. |  | X |  |  | Guilherme Franco
| Get the informations from all the tasks. |  | X |  |  | Francisco Vale
| Use the data from the tasks to create the burndown chart. |  | X |  |  | Francisco Vale
| Edit the looks of the chart to be more look alike a burndown chart. |  | X |  |  | Francisco Vale
| Implement Feature 2 (Google Calendar Integration) |  | X |  |  | Pedro Gouveia ¦ Tiago Francisco ¦ Luís Abreu
| Make the needed dependencies work |  | X |  |  | Pedro Gouveia
| Add "Google Calendar" option in the export options |  | X |  |  | Luís Abreu
| Add functionality for the user to login or if already loggen in to change account |  | X |  |  | Pedro Gouveia
| Add button to help the user interact with login functionalities |  | X |  |  | Tiago Francisco
| Remove document browser in the second step of the export functionality |  |  |  | X | Luís Abreu
| As the user clicks "Ok", create events in Google Calendar of the logged in user |  | X |  |  | Pedro Gouveia
| Don't allow the user to export to Google Calendar if no account is connected |  | X |  |  | Tiago Francisco
| Create J-Unit Tests | X |  |  |  | Every member
| Record Video | X |  |  |  | Every Member
Day 5 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Update Scrum_Master_Log |  |  |  | X | Guilherme Franco
| Update Scrum_board with Sprint 3 | X |  |  |  | Luís Abreu
| Create User story for feature 1 |  | X |  |  | Francisco Vale
| Create User story for feature 2 |  | X |  |  | Pedro Gouveia
| Correct problems in the use case diagrams |  |  |  | X | Every member
| Update Git with the files that were modified |  |  |  | X | Luís Abreu ¦ Guilherme Franco
| Review the metrics set report of team member 1 |  |  |  | X | Luís Abreu
| Review the metrics set report of team member 2 |  |  |  | X | Guilherme Franco
| Review the metrics set report of team member 3 |  |  |  | X | Pedro Gouveia
| Review the metrics set report of team member 4 |  |  |  | X | Tiago Francisco
| Review the metrics set report of team member 5 |  |  |  | X | Francisco Vale
| Implement Feature 1 (Burndown Chart) |  |  | X |  | Francisco Vale ¦ Guilherme Franco
| Add an option with XLSX file to the export alternatives. |  |  | X |  | Guilherme Franco
| Get the informations from all the tasks. |  |  | X |  | Francisco Vale
| Use the data from the tasks to create the burndown chart. |  |  | X |  | Francisco Vale
| Edit the looks of the chart to be more look alike a burndown chart. |  |  | X |  | Francisco Vale
| Implement Feature 2 (Google Calendar Integration) |  |  | X |  | Pedro Gouveia ¦ Tiago Francisco ¦ Luís Abreu
| Make the needed dependencies work |  |  | X |  | Pedro Gouveia
| Add "Google Calendar" option in the export options |  |  | X |  | Luís Abreu
| Add functionality for the user to login or if already loggen in to change account |  |  | X |  | Pedro Gouveia
| Add button to help the user interact with login functionalities |  |  | X |  | Tiago Francisco
| Remove document browser in the second step of the export functionality |  |  |  | X | Luís Abreu
| As the user clicks "Ok", create events in Google Calendar of the logged in user |  |  | X |  | Pedro Gouveia
| Don't allow the user to export to Google Calendar if no account is connected |  |  | X |  | Tiago Francisco
| Create J-Unit Tests |  | X |  |  | Every member
| Record Video | X |  |  |  | Every Member
Day 6 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Update Scrum_Master_Log |  |  |  | X | Guilherme Franco
| Update Scrum_board with Sprint 3 |  |  |  | X | Luís Abreu
| Create User story for feature 1 |  |  |  | X | Francisco Vale
| Create User story for feature 2 |  |  |  | X | Pedro Gouveia
| Correct problems in the use case diagrams |  |  |  | X | Every member
| Update Git with the files that were modified |  |  |  | X | Luís Abreu ¦ Guilherme Franco
| Review the metrics set report of team member 1 |  |  |  | X | Luís Abreu
| Review the metrics set report of team member 2 |  |  |  | X | Guilherme Franco
| Review the metrics set report of team member 3 |  |  |  | X | Pedro Gouveia
| Review the metrics set report of team member 4 |  |  |  | X | Tiago Francisco
| Review the metrics set report of team member 5 |  |  |  | X | Francisco Vale
| Implement Feature 1 (Burndown Chart) |  |  |  | X | Francisco Vale ¦ Guilherme Franco
| Add an option with XLSX file to the export alternatives. |  |  |  | X | Guilherme Franco
| Get the informations from all the tasks. |  |  |  | X | Francisco Vale
| Use the data from the tasks to create the burndown chart. |  |  |  | X | Francisco Vale
| Edit the looks of the chart to be more look alike a burndown chart. |  |  |  | X | Francisco Vale
| Implement Feature 2 (Google Calendar Integration) |  |  |  | X | Pedro Gouveia ¦ Tiago Francisco ¦ Luís Abreu
| Make the needed dependencies work |  |  |  | X | Pedro Gouveia
| Add "Google Calendar" option in the export options |  |  |  | X | Luís Abreu
| Add functionality for the user to login or if already loggen in to change account |  |  |  | X | Pedro Gouveia
| Add button to help the user interact with login functionalities |  |  |  | X | Tiago Francisco
| Remove document browser in the second step of the export functionality |  |  |  | X | Luís Abreu
| As the user clicks "Ok", create events in Google Calendar of the logged in user |  |  |  | X | Pedro Gouveia
| Don't allow the user to export to Google Calendar if no account is connected |  |  |  | X | Tiago Francisco
| Create J-Unit Tests |  |  | X |  | Every member
| Record Video |  | X |  |  | Every Member
Day 7 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Update Scrum_Master_Log |  |  |  | X | Guilherme Franco
| Update Scrum_board with Sprint 3 |  |  |  | X | Luís Abreu
| Create User story for feature 1 |  |  |  | X | Francisco Vale
| Create User story for feature 2 |  |  |  | X | Pedro Gouveia
| Correct problems in the use case diagrams |  |  |  | X | Every member
| Update Git with the files that were modified |  |  |  | X | Luís Abreu ¦ Guilherme Franco
| Review the metrics set report of team member 1 |  |  |  | X | Luís Abreu
| Review the metrics set report of team member 2 |  |  |  | X | Guilherme Franco
| Review the metrics set report of team member 3 |  |  |  | X | Pedro Gouveia
| Review the metrics set report of team member 4 |  |  |  | X | Tiago Francisco
| Review the metrics set report of team member 5 |  |  |  | X | Francisco Vale
| Implement Feature 1 (Burndown Chart) |  |  |  | X | Francisco Vale ¦ Guilherme Franco
| Add an option with XLSX file to the export alternatives. |  |  |  | X | Guilherme Franco
| Get the informations from all the tasks. |  |  |  | X | Francisco Vale
| Use the data from the tasks to create the burndown chart. |  |  |  | X | Francisco Vale
| Edit the looks of the chart to be more look alike a burndown chart. |  |  |  | X | Francisco Vale
| Implement Feature 2 (Google Calendar Integration) |  |  |  | X | Pedro Gouveia ¦ Tiago Francisco ¦ Luís Abreu
| Make the needed dependencies work |  |  |  | X | Pedro Gouveia
| Add "Google Calendar" option in the export options |  |  |  | X | Luís Abreu
| Add functionality for the user to login or if already loggen in to change account |  |  |  | X | Pedro Gouveia
| Add button to help the user interact with login functionalities |  |  |  | X | Tiago Francisco
| Remove document browser in the second step of the export functionality |  |  |  | X | Luís Abreu
| As the user clicks "Ok", create events in Google Calendar of the logged in user |  |  |  | X | Pedro Gouveia
| Don't allow the user to export to Google Calendar if no account is connected |  |  |  | X | Tiago Francisco
| Create J-Unit Tests |  |  |  | X | Every member
| Record Video |  |  |  | X | Every Member