## Week1
Day 1 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Identificar Design Patterns | x |  |  |  | Every Member
| Identificar Smell Codes | x |  |  |  | Every Member
| Fazer revisão do trabalho do respetivo colega | x |  |  |  | Every Member
| Criar MergeDoc com os code Smells e Patterns todos | x |  |  |  | Francisco Vale
| Criar MergeDoc com as reviews todos | x |  |  |  | Tiago Francisco
| Criar Sprint Backlog |  | x |  |  | Guilherme Franco
| Criar BurnOutChart |  | x |  |  | Guilherme Franco
| Criar Scrum Master Log | x |  |  |  | Luís Abreu
| Criar Work Breakdown Structure | x |  |  |  | Pedro Gouveia
Day 2 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Identificar Design Patterns |  | x |  |  | Every Member
| Identificar Smell Codes |  | x |  |  | Every Member
| Fazer revisão do trabalho do respetivo colega | x |  |  |  | Every Member
| Criar MergeDoc com os code Smells e Patterns todos | x |  |  |  | Francisco Vale
| Criar MergeDoc com as reviews todos | x |  |  |  | Tiago Francisco
| Criar Sprint Backlog |  |  |  | x | Guilherme Franco
| Criar BurnOutChart |  |  |  | x | Guilherme Franco
| Criar Scrum Master Log | x |  |  |  | Luís Abreu
| Criar Work Breakdown Structure | x |  |  |  | Pedro Gouveia
Day 3 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Identificar Design Patterns |  | x |  |  | Every Member
| Identificar Smell Codes |  | x |  |  | Every Member
| Fazer revisão do trabalho do respetivo colega | x |  |  |  | Every Member
| Criar MergeDoc com os code Smells e Patterns todos | x |  |  |  | Francisco Vale
| Criar MergeDoc com as reviews todos | x |  |  |  | Tiago Francisco
| Criar Sprint Backlog |  |  |  | x | Guilherme Franco
| Criar BurnOutChart |  |  |  | x | Guilherme Franco
| Criar Scrum Master Log | x |  |  |  | Luís Abreu
| Criar Work Breakdown Structure | x |  |  |  | Pedro Gouveia
Day 4 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Identificar Design Patterns |  | x |  |  | Every Member
| Identificar Smell Codes |  | x |  |  | Every Member
| Fazer revisão do trabalho do respetivo colega |  | x |  |  | Every Member
| Criar MergeDoc com os code Smells e Patterns todos | x |  |  |  | Francisco Vale
| Criar MergeDoc com as reviews todos | x |  |  |  | Tiago Francisco
| Criar Sprint Backlog |  |  |  | x | Guilherme Franco
| Criar BurnOutChart |  |  |  | x | Guilherme Franco
| Criar Scrum Master Log | x |  |  |  | Luís Abreu
| Criar Work Breakdown Structure | x |  |  |  | Pedro Gouveia
Day 5 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Identificar Design Patterns |  |  | x |  | Every Member
| Identificar Smell Codes |  |  | x |  | Every Member
| Fazer revisão do trabalho do respetivo colega |  | x |  |  | Every Member
| Criar MergeDoc com os code Smells e Patterns todos | x |  |  |  | Francisco Vale
| Criar MergeDoc com as reviews todos | x |  |  |  | Tiago Francisco
| Criar Sprint Backlog |  |  |  | x | Guilherme Franco
| Criar BurnOutChart |  |  |  | x | Guilherme Franco
| Criar Scrum Master Log | x |  |  |  | Luís Abreu
| Criar Work Breakdown Structure | x |  |  |  | Pedro Gouveia
Day 6 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Identificar Design Patterns |  |  |  | x | Every Member
| Identificar Smell Codes |  |  |  | x | Every Member
| Fazer revisão do trabalho do respetivo colega |  |  | x |  | Every Member
| Criar MergeDoc com os code Smells e Patterns todos |  |  | x |  | Francisco Vale
| Criar MergeDoc com as reviews todos | x |  |  |  | Tiago Francisco
| Criar Sprint Backlog |  |  |  | x | Guilherme Franco
| Criar BurnOutChart |  |  |  | x | Guilherme Franco
| Criar Scrum Master Log |  | x |  |  | Luís Abreu
| Criar Work Breakdown Structure |  | x |  |  | Pedro Gouveia
Day 7 | Tasklist | TODO | In progress | Reviewing | Done | Member
| Identificar Design Patterns |  |  |  | x | Every Member
| Identificar Smell Codes |  |  |  | x | Every Member
| Fazer revisão do trabalho do respetivo colega |  |  |  | x | Every Member
| Criar MergeDoc com os code Smells e Patterns todos |  |  |  | x | Francisco Vale
| Criar MergeDoc com as reviews todos |  |  |  | x | Tiago Francisco
| Criar Sprint Backlog |  |  |  | x | Guilherme Franco
| Criar BurnOutChart |  |  |  | x | Guilherme Franco
| Criar Scrum Master Log |  |  |  | x | Luís Abreu
| Criar Work Breakdown Structure |  |  |  | x | Pedro Gouveia