## Folha1
Backlog ID | User Story ID | Estimated Duration | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Update Scrum_Master_Log | 1 | 1 | bar: Day 2
Update Scrum_board | 2 | 2 | bar: Day 2 to Day 3
Create first Sprint_Backlog | 3 | 2 | bar: Day 2 to Day 3
Create second Sprint_Backlog | 4 | 2 | bar: Day 2 to Day 3
Distribute metrics between the members | 5 | 2 | bar: Day 2 to Day 3
Create Report about metrics set 1 | 6 | 2 | bar: Day 3 to Day 4
Create Report about metrics set 2 | 7 | 2 | bar: Day 3 to Day 4
Create Report about metrics set 3 | 8 | 2 | bar: Day 3 to Day 4
Create Report about metrics set 4 | 9 | 2 | bar: Day 3 to Day 4
Create Report about metrics set 5 | 10 | 2 | bar: Day 3 to Day 4
Review the metrics set report of team member 1 | 11 | 3 | bar: Day 5 to Day 7
Review the metrics set report of team member 2 | 12 | 3 | bar: Day 5 to Day 7
Review the metrics set report of team member 3 | 13 | 3 | bar: Day 5 to Day 7
Review the metrics set report of team member 4 | 14 | 3 | bar: Day 5 to Day 7
Review the metrics set report of team member 5 | 15 | 3 | bar: Day 5 to Day 7
| Idealized Burn | 34 | 29 | 24 | 19 | 14 | 9 | 4 | 0
| Actual burned | 34 | 34 | 29 | 20 | 15 | 10 | 5 | 0