## Folha1
Project name: | Gantt Project
Level | Task
1 | Phase 1 | Phase 2
1.1 | Setup the Gantt Project
1.2 | Study and extract exhaustive information from the existing source code
1.3 | Organize Scrum
1.2.1 | Detect GoF Design Patterns
1.2.2 | Detect code smells
1.2.3 | Review design patterns and code smells
1.3.1 | Create MergeDoc with code smells and design patterns
1.3.2 | Create MergeDoc with all reviews
1.3.3 | Create Spring backlog
1.3.4 | Create Burnout Chart
1.3.5 | Create Scrum Master Log
1.3.6 | Create Work Breakdown Structure
2 | Phase 2
2.1 | Update Scrum_Master_Log
2.2 | Update Scrum_board
2.3 | Create first Sprint_Backlog
2.4 | Distribute use cases of the ganttproject between the members
2.4.1 | Create report about use case, must have the diagram and all the details about the use case set 1
2.4.2 | Create report about use case, must have the diagram and all the details about the use case set 2
2.4.3 | Create report about use case, must have the diagram and all the details about the use case set 3
2.4.4 | Create report about use case, must have the diagram and all the details about the use case set 4
2.4.5 | Create report about use case, must have the diagram and all the details about the use case set 5
2.5 | Distribute metrics between the members
2.5.1 | Create Report about metrics set 1
2.5.2 | Create Report about metrics set 2
2.5.3 | Create Report about metrics set 3
2.5.4 | Create Report about metrics set 4
2.5.5 | Create Report about metrics set 5
2.6.1 | Review the use case diagram and its analysis of a member team member 1
2.6.2 | Review the use case diagram and its analysis of a member team member 2
2.6.3 | Review the use case diagram and its analysis of a member team member 3
2.6.4 | Review the use case diagram and its analysis of a member team member 4
2.6.5 | Review the use case diagram and its analysis of a member team member 5
2.7.1 | Create user Story about feature 1
2.7.2 | Create user Story about feature 2
2.8.1 | Implement Feature 1 (Burndown Chart)
2.8.2 | Implement Feature 2 (Google Calendar Integration)