## Folha1
Backlog ID | User Story ID | Estimated Duration | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
Distribute use cases of the ganttproject between the members | 1 | 1 |  | 1
Create report about use case, must have the diagram and all the details about the use case set 1 | 2 | 2 |  |  | 1 | 1
Create report about use case, must have the diagram and all the details about the use case set 2 | 3 | 2 |  |  | 1 | 1
Create report about use case, must have the diagram and all the details about the use case set 3 | 4 | 2 |  |  | 1 | 1
Create report about use case, must have the diagram and all the details about the use case set 4 | 5 | 2 |  |  | 1 | 1
Create report about use case, must have the diagram and all the details about the use case set 5 | 6 | 2 |  |  |  |  | 1 | 1
Review the use case diagram and its analysis of a member team member 1 | 7 | 2 |  |  |  |  | 1 |  | 1
Review the use case diagram and its analysis of a member team member 2 | 8 | 2 |  |  |  |  | 1 | 1
Review the use case diagram and its analysis of a member team member 3 | 9 | 2 |  |  |  |  | 1 | 1
Review the use case diagram and its analysis of a member team member 4 | 10 | 2 |  |  |  |  | 1 | 1
Review the use case diagram and its analysis of a member team member 5 | 11 | 2 | [5 empty] | 1 | 1
| Idealized Burn | 21 | 18 | 15 | 12 | 9 | 6 | 3 | 0
| Actual burned | 21 | 21 | 20 | 16 | 12 | 7 | 2 | 0